## Instructions
Add a tab for the new week
Copy the template from the previsous sheet

## Jan 22-Feb 2
Items | Update
Date on which you worked on the project. | 1/23/2026, 1/28/2026
Number of hours spent on that day. | 3 hours (1/23), 1 hour (1/28)
Type of component, implementation or document. | Project Charter
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Goals, Deliverables, Success Measurements, Stakeholders (partial)
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Filled out the above listed sections of our project charter 2. Collaborated with teammates to proofread the document for any errors 3. Helped create GitHub repository and documented weekly log
Total number of hours worked during the week. | 4 hours

## Feb 2-Feb 9
Items | Update
Date on which you worked on the project. | 2/02/2026, 2/04/2026, 2/06/2026
Number of hours spent on that day. | 1 hour (2/2), 2 hours (2/4), 1 hour (2/6)
Type of component, implementation or document. | SRS Document
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | User Case Stories & Functional Requirements
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Creating User Case Stories for our application 2. Identifying required features based on the generated User Case Stories 3. Deciding the stimuli, responses, and requirements for these features
Total number of hours worked during the week. | 4

## Feb 9 - Feb 16
Items | Update
Date on which you worked on the project. | 2/09/2026, 2/11/2026, 2/13/2026
Number of hours spent on that day. | 1 hour (2/9), 2 hours (2/11), 2 hour (2/13)
Type of component, implementation or document. | SRS Document
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | User Case Stories & Functional Requirements
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Filling out subsections in section one of SRS Document 2. Filling out subsections in section two of SRS Document 3. Filling out 3.2.4, 3.2.5, and 3.2.6
Total number of hours worked during the week. | 5

## Feb 16 - Feb 23
Items | Update
Date on which you worked on the project. | 2/16/2026, 2/18/2026, 2/20/2026
Number of hours spent on that day. | 1 hour (2/16), 2 hours (2/18), 3 hour (2/20)
Type of component, implementation or document. | SRS Document
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | User Case Stories & Functional Requirements
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Completing Section One of SRS Document (With additional refinement from Stephen) 2. Completing Section Two of SRS Document (With additional refinement from Stephen) 3. Completing Section One of SRS Document
Total number of hours worked during the week. | 6

## Feb 23 - Mar 3
Items | Update
Date on which you worked on the project. | 2/25/20206, 2/27/2027
Number of hours spent on that day. | 0.5 hour (2/25), 1 hours (2/27)
Type of component, implementation or document. | Design Document
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Section 2: System Architecture Description
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Reviewing how to create the required diagrams 2. Planning out Use Case and User Interface diagrams with Steven
Total number of hours worked during the week. | 1.5

## Mar 16 - Mar 23
Items | Update
Date on which you worked on the project. | 3/18/20206, 2/20/2027
Number of hours spent on that day. | 1 hour (3/18), 1 hours (3/20)
Type of component, implementation or document. | Tracibility Matrix Document
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Full Document
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Completing the first matrix of the Tracibility Document 2. Completing the second matrix of the Tracibility Document
Total number of hours worked during the week. | 2

## Mar 23 - Mar 30
Items | Update
Date on which you worked on the project. | 3/22/2026, 3/25/2026, 3/27/2026
Number of hours spent on that day. | 1 Hours (3/23), 2 Hours (3/25) 2.5 Hours (3/27)
Type of component, implementation or document. | Sprint 1 Slice
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Database Project & Project Manager Entities, Project Creation Interface, Project Creation Method
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Created database entities to store project details and their associated project managers 2. Created a project creation interface page, the method used to take info from that page and add it to the database, and the method to transfer the use from the dashboard to that page 3. Presented the sprint 1 prototype
Total number of hours worked during the week. | 5.5