## Instructions
Add a tab for the new week
Copy the template from the previsous sheet

## Jan 22-Feb 2
Items | Update
Date on which you worked on the project. | 1/23/2026. 1/28/2026, 02/02/2026
Number of hours spent on that day. | 3 hours (1/23), 1 hour (1/28), 30 minutes (02/02)
Type of component, implementation or document. | Project Charter, SRS
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Abstract, Project Summary, Goals/Objectives, Stakeholders, Out-of-Scope, Risks/Constraints/Assumptions
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Wrote the abstract, introduction, out-of-scope, risks/constraints/assumptions sections of the charter. (1/23) 2. Worked with Owen and Pedro to clarify the deliverables and success measurements sections. (1/23) 3. Created repository and worked on project updates spreadsheet. (1/28) 4. Created user stories for SRS and updated spreadsheet. (02/02),
Total number of hours worked during the week. | 4.5 hours

## Feb 2-9
Items | Update
Date on which you worked on the project. | 02/04/2026, 02/06/2026, 02/09/2026
Number of hours spent on that day. | .5 hr (02/04), 1 hr (02/06), 1.5 hrs (02/09)
Type of component, implementation or document. | SRS
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Introduction, features and use cases
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Wrote user stories with both other group members. 2. Translated user stories 1-6 to features with Owen. 3. Delegated features among the group to members to create use cases. 4. Wrote project update for 02/02-02/09
Total number of hours worked during the week. | 3 hours

## Feb 9-16
Items | Update
Date on which you worked on the project. | 02/11/2026, 02/13/2026, 02/16/2026
Number of hours spent on that day. | .5 hr (02/11), .5 hr (02/13), 2 hrs (02/16)
Type of component, implementation or document. | SRS
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Features and Use Cases
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Wrote feature 1 description and stimulus with Owen and Pedro. (02/11) 2. Explained section formatting and details to teammates to ensure correctness. (02/13) 3. Wrote feature 1 functional requirements and REQ's. (02/13) 4. Wrote weekly log and finished feature information for features 1 and 2. (02/16)
Total number of hours worked during the week. | 3 hours

## Feb 16-23
Items | Update
Date on which you worked on the project. | 02/18/2026, 02/19/2026, 02/20/2026
Number of hours spent on that day. | 1 hr (02/18), 4 hrs (02/19), 8 hrs (02/20)
Type of component, implementation or document. | SRS
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Section 3.2 Features, Section 3.3 Use Cases, Section 4.1 Sequence Diagrams
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Completed Section 3.2.2 - 3.2.5 (02/18) 2. Completed Section 3.2.6 - 3.2.10, Use Cases 1-9 (02/19) 3. Competed Use Cases 10-12 and the totality of Section 4.1 (02/20) 4. Proof-read and fixed other sections to ensure logical consistency throughout the SRS (02/20)
Total number of hours worked during the week. | 13 hours

## Feb 23-Mar 2
Items | Update
Date on which you worked on the project. | 02/25/2026, 02/27/2026, 03/02/2026
Number of hours spent on that day. | .5 hrs (02/25), .5 (02/27), 1 hr (03/02)
Type of component, implementation or document. | SDS
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Domain Models
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Divided work among the group (02/25) 2. Created domain model for UC-01 Create Account (02/27) 3. Created domain model for UC-04 Create Project (03/02) 4. Refined domain models and started SDS work. (03/02)
Total number of hours worked during the week. | 2 hours